## Sheet1
Type | Description | Size | mvp | status
Tech | Authorization (email/password) | L | y | done
Feature | Register as Coach and/or parent | M | y | done
Feature | Add Team as manager | M | y | done
Feature | Manage Fixtures as manager | M | y | done
Feature | Manage Events as manager | M | y | done
Feature | Manage Posts as manager | M | y | done
Feature | Manage kit/player requests as manager | M | y | done
Feature | Manage Dependents as parent | M | y | done
Feature | Associate dependent with team as parent | M | y | done
Feature | Confirm availability as parent | M | y | done
Feature | See club match results on dashboard | M | y | done
Feature | See Upcoming fixtures on dashboard | M | y | done
Feature | See team events on dashboard | M | y | done
Feature | See player stats on dashboard | M | y | done
Feature | See posts on dashboard | M | y | done
Feature | Manage profile | M | y | done
Feature | Update fixture result | M | y | done
Tech | Authorisation using external id | M | y | done
Tech | Create Android App | L | n | ready
Tech | Create Ios App | L | n | ready
Feature | Manage fixtures as fixture seretary | M | n | ready
Feature | Manage Club as club manager | M | n | ready
Feature | Manage Events (social, meetings) as club manager | M | n | ready
Tech | Remove Tailwind CSS and tidy code | M | n | ready
Feature | Manage Payments (integrate with TeamFeePay) | M | n | ready
Feature | Manage Parent details (consent, emergency contacts, address, etc.) as parent | M | n | ready
Feature | Manage Coach details (DBS and safeguarding) | M | n | ready
Feature | Notifications by dashboard | M | n | ready
Feature | Notifications by email | M | n | ready
Feature | Reports and analytics (attentdance, stats, etc.) | M | n | ready
Feature | Media gallery & upload photos for social media | M | n | ready
Feature | Wiki (onboarding checklists, guidance, How-to guides, etc.) | M | n | ready
Feature | Club branding | M | n | ready
Feature | Manage venues for training (location & timing) as club manager | M | n | ready
Feature | Request and assign referee and for fixture | M | n | ready